## Draft Budget - Part A
Summary
Project | Infrastructure Upgrade
Total Budget
S. No. | Item | Budgeted Cost | Remarks
1 | Equipment | 50000 | the cost of equipment may vary.
2 | DELL R910 X 2 | 45000 | the cost of it may vary.
3 | EMC Clarion CX700 | 60000 | the cost of it may vary.
4 | Cabling CAT 6A / electrical | 70000 | the cost of it may vary.
5 | Fibre SAN switches | 25000 | the cost of it may vary.
6 | Human resources | 60000 | the cost of it may vary.
7 | Service Cost | 40000 | the cost of it may vary.
8 | Software | 65000 | the cost of it may vary.
9 | Fees and Charges | 15000 | the cost of it may vary.
10
11
12
13
14
15
Total Budget |  | 430000
* after completing the calculations please submit this file as a .PDF document.

## Budget Variance - Part C
Summary
Project | Infrastructure Upgrade
Total Budget
S. No. | Item | Budgeted Cost | Actual | Variance | Favourable /Unfavourable | Remarks
1 | Equipment | 50000 | 60000 | -10000 | unfavourable | due to non-availablity of certain hardware, there is an increasse in the cost of $10000.
2 | DELL R910 X 2 | 45000 | 45000 |  | favourable | it reflects a favourable cost and falls under the budget.
3 | EMC Clarion CX700 | 60000 | 60000 |  | favourable | it reflects a favourable cost and falls under the budget.
4 | Cabling CAT 6A / electrical | 70000 | 70000 |  | favourable | it reflects a favourable cost and falls under the budget.
5 | Fibre SAN switches | 25000 | 25000 |  | favourable | it reflects a favourable cost and falls under the budget.
6 | Human resources | 60000 | 68000 | -80000 | unfavourable | additional staff hired for $8000
7 | Service Cost | 40000 | 40000 |  | favourable | it reflects a favourable cost and falls under the budget.
8 | Software | 65000 | 62000 | 3000 | favourable | there was a free offer available through which we saved $3000.
9 | Fees and Charges | 15000 | 15000 |  | favourable | it reflects a favourable cost and falls under the budget.
10 |  |  |  | 0
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0
Total |  | 430000 | 445000 |  | unfavourable | it reflects an unfavourable balance of 15000
* after completing the calculations please submit this file as a .PDF document.